## 1
Please ensure this tracking sheet is completed as a group, as it will be used to monitor your individual participation within the team.
Team Members | Role/ Responsibilty | Email
Andrew Alier | Entity Relationship Diagram | a.alier@alustudent.com
ISHIMWE Jonathan | SQL Database Implementation | j.ishimwe4@alustudent.com
ITANGISHAKA Olivier | JSON Data Modeling | o.itangisha@alustudent.com
Task Allocation and Tracker
| Task Allocated | Assigned Member | Deadline | Completion Status (Not Started/In Progress/Completed/Did not participate) | Reviewed by Team? (Yes/No) | Comments
| Analyzing XML Data structure and creating ERD | Andrew Alier | 2026-01-24 | In progress
| Transforming ERD to a working MySQL database | ISHIMWE Jonathan | 2026-01-24 | Completed | Yes
| Designing JSON schemas that represent your database entities | Olivier ITANGISHAKA | 2026-01-25 | In progress
|  | [Name] | [Date]
|  | [Name] | [Date]
|  | [Name] | [Date]
|  | [Name] | [Date]
|  | [Name] | [Date]
|  | [Name] | [Date]
Meeting Attendance Log
Meeting Date | Agenda | Facilitator | Attendees | Key Discussion Points | Next Steps
2026-01-22 |  | [Name] | Andrew Alier Jonathan ISHIMWE Olivier ITANGISHAKA | Database Design and Implementation assignment review, and task allocation. | [Follow-up Actions]
[Date] |  | [Name] | [List of Attendees] | [Summary of Discussion] | [Follow-up Actions]
[Date] |  | [Name] | [List of Attendees] | [Summary of Discussion] | [Follow-up Actions]
[Date] |  | [Name] | [List of Attendees] | [Summary of Discussion] | [Follow-up Actions]
[Date] |  | [Name] | [List of Attendees] | [Summary of Discussion] | [Follow-up Actions]